## test plan
What are we testing?
Functional testing of garage block
How are we going to test?
The documentation is presented in full. We are going to do functional and non-functional testing. At the functional stage, we use - black box. At the stage of non-functional testing - usability. Integration testing to check interactions between modules. Do alpha testing. UI and UX testing
When is testing?
Product Analysis | 5 h
Designing Test Strategy | 4 h
Defining Objectives | 4 h
Establish Test Criteria | 2 h
Planning Resource Allocation | 3 h
Planning Setup of Test Environment | 2 h
Determining Test Schedule and Estimation | 3 h
Establish Test Deliverables | 3 h
Alpha testing | 3 h
Testers |  | Estimated time | Real time | Metrics | Steps
Integration testing | Solomia | 15 | 16 | 6.667% | Product Analysis | 6 h
System testing | Alice |  |  |  | Designing Test Strategy | 4 h
Functional testing | Mike |  |  |  | Defining Objectives | 4 h
Non-functional testing | Tony |  |  |  | Establish Test Criteria | 3 h
Alpha testing | Jake
UI and UX testing | Stephania
Report | Mike
Deliverables required before testing
1. The test environment is ready for testing
2. Functionality is 100% complete
3. Test design
4. Test plan
Deliverables required after testing
1. Defect Reports
2. Test Results